## Flow Chart
MLA Environment Reliability Test Flow Chart
Total Samples | 1-93 + EMC dedicated samples
Baseline Optical | 7 days
Post-group Optical | 2 days / group
L1/L4 Rule | Group A = 3 days; others = 2 days
Known Total Summed Time | 520.8 days + EMC
Known Total Elapsed Time | >= 155.4 days + EMC
Baseline
Seq | Test Item | Standard | Sample No. | Time (d) | Type | Note
1 | Baseline Optical Test | TPJLR-13-001 / STJLR.13.5009 | 1-68 | 7 | Baseline | Pre-test unified optical test
2 | Baseline L1/L4 | TPJLR.18.125 L1/L4 | 1-68 | 3 | Baseline | Pre-test baseline functional/performance eval
Baseline Subtotal |  |  |  | 10
Group A
Seq | Test Item | Standard | Sample No. | Time (d) | Type | Note
A1 | Particle Exposure | TPJLR.15.051 | 1-12 | 1.2 | Estimated from standard
A2 | Low Temperature Exposure | K1 | 1-12 | 2 | Timing plan reference
A3 | High Temperature Exposure | K2 | 1-12 | 2 | Timing plan reference
A4 | Low Temperature Operation | K3 | 1-12 | 2 | Timing plan reference
A5 | High Temperature Operation | K4 | 1-12 | 5 | Timing plan reference
A6 | Temperature Step Test | K5 | 1-12 | 2 | Timing plan reference
A7 | Powered Thermal Cycle | K6 | 1-12 | 11 | Timing plan reference
A8 | Thermal Shock in Air | K7 | 1-12 | 14 | Timing plan reference
A9 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed: Group A = 3d
A10 | Vibration | K15 | 1-12 | 7 | Timing plan reference
A11 | Mechanical Shock - Package Drop | K16.1 | 1-14 | 2 | Timing plan reference
A12 | Mechanical Shock - Low | K16.4 | 1-12 | 2 | Timing plan reference
A13 | Audible Noise | K17 | 1-12 | 10 | Timing plan reference
A14 | Humidity Temperature Cycle | K9 | 1-12 | 12 | Timing plan reference
A15 | Water/Fluid Ingress | K10 | 1-12 | 3 | Timing plan reference
A16 | Dust Ingress | K13 | 1-12 | 5 | Timing plan reference
A17 | Dust Blowing | K14 | 1-12 | 0.2 | Estimated from standard
A18 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed: Group A = 3d
A19 | Optical Test | TPJLR-13-001 | 1-12 | 2 | User confirmed: post-group optical = 2d
A20 | Internal Inspection | L6 | 1-12 | 7 | Timing plan reference
Group A Subtotal |  |  |  | 95.4
Group B
Seq | Test Item | Standard | Sample No. | Time (d) | Type | Note
B1 | Chemical Resistance | K22 | 15-26 | 5 | Timing plan reference
B2 | Connector and Lead/Lock Strength | K18 | 15-26 | 7 | Timing plan reference
B3 | L1/L4 | TPJLR.18.125 L1/L4 | 15-26 | 2 | User confirmed: non-A groups = 2d
B4 | Optical Test | TPJLR-13-001 | 15-26 | 2 | User confirmed: post-group optical = 2d
B5 | Internal Inspection | L6 | 15-26 | 4 | Timing plan reference
Group B Subtotal |  |  |  | 20
Group C
Seq | Test Item | Standard | Sample No. | Time (d) | Type | Note
C1 | Thermal Shock in Air | K7 | 27-32 | 14 | Timing plan reference
C2 | Particle Exposure | TPJLR.15.051 | 27-32 | 1.2 | Estimated from standard
C3 | Vibration | K15 | 27-32 | 4 | Timing plan reference
C4 | Dust Ingress | K13 | 27-32 | 2 | Timing plan reference
C5 | Dust Blowing | K14 | 27-32 | 0.2 | Estimated from standard
C6 | Mechanical Wear-Out | K26 | 27-32 | 23 | Timing plan reference
C7 | L1/L4 | TPJLR.18.125 L1/L4 | 27-32 | 2 | User confirmed: non-A groups = 2d
C8 | Optical Test | TPJLR-13-001 | 27-32 | 2 | User confirmed: post-group optical = 2d
C9 | Internal Inspection | L6 | 27-32 | 3 | Timing plan reference
Group C Subtotal |  |  |  | 51.4
Group D Parallel Tests Overview
D1 |  | D2 |  | D3
Samples: 33-38 Subtotal: 49.0 d Main: Corrosive Gases Post: L1/L4 + Optical Test + Internal Inspection |  | Samples: 39-44 Subtotal: 9.0 d Main: Solar Radiation Post: L1/L4 + Optical Test + Internal Inspection |  | Samples: 45-52 Subtotal: 68.0 d Main: Thermal Shock Endurance Post: L1/L4 + Internal Inspection
D4 |  | D5 |  | D6
Samples: 45-50 Subtotal: 7.0 d Main: Dewing Test Post: L1/L4 + Internal Inspection |  | Samples: 51-56 Subtotal: 49.0 d Main: High Temperature Endurance Post: L1/L4 + Optical Test + Internal Inspection |  | Samples: 65-70 Subtotal: 47.0 d Main: 85/85 HTHH Endurance Post: L1/L4 + Internal Inspection
D7 |  | D8 |  | D9
Samples: 57-62 Subtotal: 53.0 d Main: 60/95 HTHH Endurance Post: L1/L4 + Optical Test + Internal Inspection |  | Samples: 77-82 Subtotal: No Test Main: HALT Post: L1/L4 + Optical Test + Internal Inspection |  | Samples: 63-68 Subtotal: 12.0 d Main: Condensing Humidity Post: L1/L4 + Optical Test + Internal Inspection
Notes
Solar Radiation / Corrosive Gases / Thermal Shock Endurance are currently aligned to the L481 timing plan, not pure standard-duration math.
D8 remains marked as No Test because the current MLA source flow chart marks HALT as No Test.
EMC duration is intentionally left TBD and should stay as an independent plan.

## Timing Summary
MLA Test Timing Summary
Group | Sample Scope | Known Subtotal (d) | Mode
Baseline | 1-68 | 10 | Sequential
Group A | 1-12 | 95.4 | Sequential
Group B | 15-26 | 20 | Sequential
Group C | 27-32 | 51.4 | Sequential
D1 | 33-38 | 49 | Parallel subgroup
D2 | 39-44 | 9 | Parallel subgroup
D3 | 45-52 | 68 | Parallel subgroup
D4 | 45-50 | 7 | Parallel subgroup
D5 | 51-56 | 49 | Parallel subgroup
D6 | 65-70 | 47 | Parallel subgroup
D7 | 57-62 | 53 | Parallel subgroup
D8 | 77-82 | 0 | Parallel subgroup
D9 | 63-68 | 12 | Parallel subgroup
Group E | Per EMC plan | TBD | Sequential
Group F | Based on actual tests | 50 | Sequential
Known Total Summed Time |  | 520.8
Known Total Elapsed Time |  | >= 155.4 + EMC

## Detailed List
Group | Seq | Test Item | Standard | Sample No. | Time (d) | Basis / Note
Baseline |  | Baseline Optical Test | TPJLR-13-001 / STJLR.13.5009 | 1-68 | 7 | Pre-test unified optical test
Baseline |  | Baseline L1/L4 | TPJLR.18.125 L1/L4 | 1-68 | 3 | Pre-test baseline functional/performance eval
Group A | A1 | Particle Exposure | TPJLR.15.051 | 1-12 | 1.2 | Estimated from standard
Group A | A2 | Low Temperature Exposure | K1 | 1-12 | 2 | Timing plan reference
Group A | A3 | High Temperature Exposure | K2 | 1-12 | 2 | Timing plan reference
Group A | A4 | Low Temperature Operation | K3 | 1-12 | 2 | Timing plan reference
Group A | A5 | High Temperature Operation | K4 | 1-12 | 5 | Timing plan reference
Group A | A6 | Temperature Step Test | K5 | 1-12 | 2 | Timing plan reference
Group A | A7 | Powered Thermal Cycle | K6 | 1-12 | 11 | Timing plan reference
Group A | A8 | Thermal Shock in Air | K7 | 1-12 | 14 | Timing plan reference
Group A | A9 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed: Group A = 3d
Group A | A10 | Vibration | K15 | 1-12 | 7 | Timing plan reference
Group A | A11 | Mechanical Shock - Package Drop | K16.1 | 1-14 | 2 | Timing plan reference
Group A | A12 | Mechanical Shock - Low | K16.4 | 1-12 | 2 | Timing plan reference
Group A | A13 | Audible Noise | K17 | 1-12 | 10 | Timing plan reference
Group A | A14 | Humidity Temperature Cycle | K9 | 1-12 | 12 | Timing plan reference
Group A | A15 | Water/Fluid Ingress | K10 | 1-12 | 3 | Timing plan reference
Group A | A16 | Dust Ingress | K13 | 1-12 | 5 | Timing plan reference
Group A | A17 | Dust Blowing | K14 | 1-12 | 0.2 | Estimated from standard
Group A | A18 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed: Group A = 3d
Group A | A19 | Optical Test | TPJLR-13-001 | 1-12 | 2 | User confirmed: post-group optical = 2d
Group A | A20 | Internal Inspection | L6 | 1-12 | 7 | Timing plan reference
Group B | B1 | Chemical Resistance | K22 | 15-26 | 5 | Timing plan reference
Group B | B2 | Connector and Lead/Lock Strength | K18 | 15-26 | 7 | Timing plan reference
Group B | B3 | L1/L4 | TPJLR.18.125 L1/L4 | 15-26 | 2 | User confirmed: non-A groups = 2d
Group B | B4 | Optical Test | TPJLR-13-001 | 15-26 | 2 | User confirmed: post-group optical = 2d
Group B | B5 | Internal Inspection | L6 | 15-26 | 4 | Timing plan reference
Group C | C1 | Thermal Shock in Air | K7 | 27-32 | 14 | Timing plan reference
Group C | C2 | Particle Exposure | TPJLR.15.051 | 27-32 | 1.2 | Estimated from standard
Group C | C3 | Vibration | K15 | 27-32 | 4 | Timing plan reference
Group C | C4 | Dust Ingress | K13 | 27-32 | 2 | Timing plan reference
Group C | C5 | Dust Blowing | K14 | 27-32 | 0.2 | Estimated from standard
Group C | C6 | Mechanical Wear-Out | K26 | 27-32 | 23 | Timing plan reference
Group C | C7 | L1/L4 | TPJLR.18.125 L1/L4 | 27-32 | 2 | User confirmed: non-A groups = 2d
Group C | C8 | Optical Test | TPJLR-13-001 | 27-32 | 2 | User confirmed: post-group optical = 2d
Group C | C9 | Internal Inspection | L6 | 27-32 | 3 | Timing plan reference
D1 | D1-1 | Corrosive Gases | K21 | 33-38 | 42 | Timing plan reference
D1 | D1-2 | L1/L4 | TPJLR.18.125 L1/L4 | 33-38 | 2 | User confirmed: non-A groups = 2d
D1 | D1-3 | Optical Test | TPJLR-13-001 | 33-38 | 2 | User confirmed: post-group optical = 2d
D1 | D1-4 | Internal Inspection | L6 | 33-38 | 3 | Timing plan reference
D2 | D2-1 | Solar Radiation | K20 | 39-44 | 2 | Timing plan reference
D2 | D2-2 | L1/L4 | TPJLR.18.125 L1/L4 | 39-44 | 2 | User confirmed: non-A groups = 2d
D2 | D2-3 | Optical Test | TPJLR-13-001 | 39-44 | 2 | User confirmed: post-group optical = 2d
D2 | D2-4 | Internal Inspection | L6 | 39-44 | 3 | Timing plan reference
D3 | D3-1 | Thermal Shock Endurance | K23 | 45-52 | 46 | Timing plan reference
D3 | D3-2 | L1/L4 | TPJLR.18.125 L1/L4 | 45-52 | 2 | User confirmed: non-A groups = 2d
D3 | D3-3 | Internal Inspection | L6 | 45-52 | 20 | Timing plan reference
D4 | D4-1 | Dewing Test | K8 | 45-50 | 2 | Timing plan reference
D4 | D4-2 | L1/L4 | TPJLR.18.125 L1/L4 | 45-50 | 2 | User confirmed: non-A groups = 2d
D4 | D4-3 | Internal Inspection | L6 | 45-50 | 3 | Timing plan reference
D5 | D5-1 | High Temperature Endurance | K24 | 51-56 | 42 | Timing plan reference
D5 | D5-2 | L1/L4 | TPJLR.18.125 L1/L4 | 51-56 | 2 | User confirmed: non-A groups = 2d
D5 | D5-3 | Optical Test | TPJLR-13-001 | 51-56 | 2 | User confirmed: post-group optical = 2d
D5 | D5-4 | Internal Inspection | L6 | 51-56 | 3 | Timing plan reference
D6 | D6-1 | 85/85 HTHH Endurance | K27 | 65-70 | 42 | Timing plan reference
D6 | D6-2 | L1/L4 | TPJLR.18.125 L1/L4 | 65-70 | 2 | User confirmed: non-A groups = 2d
D6 | D6-3 | Internal Inspection | L6 | 65-70 | 3 | Timing plan reference
D7 | D7-1 | 60/95 HTHH Endurance | K27 | 57-62 | 46 | Timing plan reference
D7 | D7-2 | L1/L4 | TPJLR.18.125 L1/L4 | 57-62 | 2 | User confirmed: non-A groups = 2d
D7 | D7-3 | Optical Test | TPJLR-13-001 | 57-62 | 2 | User confirmed: post-group optical = 2d
D7 | D7-4 | Internal Inspection | L6 | 57-62 | 3 | Timing plan reference
D8 | D8-1 | HALT | K28 | 77-82 | No Test | Current MLA flow chart marks as No Test
D8 | D8-2 | L1/L4 | TPJLR.18.125 L1/L4 | 77-82 | No Test | Current MLA flow chart marks as No Test
D8 | D8-3 | Optical Test | TPJLR-13-001 | 77-82 | No Test | Current MLA flow chart marks as No Test
D8 | D8-4 | Internal Inspection | L6 | 77-82 | No Test | Current MLA flow chart marks as No Test
D9 | D9-1 | Condensing Humidity | TPJLR.52.351 | 63-68 | 5 | 120h from standard
D9 | D9-2 | L1/L4 | TPJLR.18.125 L1/L4 | 63-68 | 2 | User confirmed: non-A groups = 2d
D9 | D9-3 | Optical Test | TPJLR-13-001 | 63-68 | 2 | User confirmed: post-group optical = 2d
D9 | D9-4 | Internal Inspection | L6 | 63-68 | 3 | Aligned to other D groups
Group E | E | EMC Test Plan | JLR-EMC-CS | Per EMC plan | TBD | Duration TBD
Group F | F1 | Restricted Substance Management | STJLR.99.9999 | Based on actual tests | 40 | Timing plan reference
Group F | F2 | Operating Noise & Transient Noise | TPJLR.00.344 | 69-93 | 10 | Timing plan reference