## Flow Chart
MLA Environment Reliability Test Flow Chart (Compatible Version)
Total Samples | 1-93 + EMC dedicated samples
Baseline Optical | 7 days
Post-group Optical | 2 days / group
L1/L4 | A = 3 days; others = 2 days
EMC | TBD
Group | Seq | Test Item | Standard | Sample No. | Time (d) | Basis / Note
Baseline |  | Optical Test | TPJLR-13-001 / STJLR.13.5009 | 1-68 | 7 | Pre-test unified optical test
Baseline |  | L1/L4 | TPJLR.18.125 L1/L4 | 1-68 | 3 | Pre-test baseline functional/performance eval
Group A | A1 | Particle Exposure | TPJLR.15.051 | 1-12 | 1.2 | Estimated from standard
Group A | A2 | Low Temperature Exposure | K1 | 1-12 | 2 | Timing plan reference
Group A | A3 | High Temperature Exposure | K2 | 1-12 | 2 | Timing plan reference
Group A | A4 | Low Temperature Operation | K3 | 1-12 | 2 | Timing plan reference
Group A | A5 | High Temperature Operation | K4 | 1-12 | 5 | Timing plan reference
Group A | A6 | Temperature Step Test | K5 | 1-12 | 2 | Timing plan reference
Group A | A7 | Powered Thermal Cycle | K6 | 1-12 | 11 | Timing plan reference
Group A | A8 | Thermal Shock in Air | K7 | 1-12 | 14 | Timing plan reference
Group A | A9 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed
Group A | A10 | Vibration | K15 | 1-12 | 7 | Timing plan reference
Group A | A11 | Mechanical Shock - Package Drop | K16.1 | 1-14 | 2 | Timing plan reference
Group A | A12 | Mechanical Shock - Low | K16.4 | 1-12 | 2 | Timing plan reference
Group A | A13 | Audible Noise | K17 | 1-12 | 10 | Timing plan reference
Group A | A14 | Humidity Temperature Cycle | K9 | 1-12 | 12 | Timing plan reference
Group A | A15 | Water/Fluid Ingress | K10 | 1-12 | 3 | Timing plan reference
Group A | A16 | Dust Ingress | K13 | 1-12 | 5 | Timing plan reference
Group A | A17 | Dust Blowing | K14 | 1-12 | 0.2 | Estimated from standard
Group A | A18 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed
Group A | A19 | Optical Test | TPJLR-13-001 | 1-12 | 2 | User confirmed
Group A | A20 | Internal Inspection | L6 | 1-12 | 7 | Timing plan reference
Group B | B1 | Chemical Resistance | K22 | 15-26 | 5 | Timing plan reference
Group B | B2 | Connector and Lead/Lock Strength | K18 | 15-26 | 7 | Timing plan reference
Group B | B3 | L1/L4 | TPJLR.18.125 L1/L4 | 15-26 | 2 | User confirmed
Group B | B4 | Optical Test | TPJLR-13-001 | 15-26 | 2 | User confirmed
Group B | B5 | Internal Inspection | L6 | 15-26 | 4 | Timing plan reference
Group C | C1 | Thermal Shock in Air | K7 | 27-32 | 14 | Timing plan reference
Group C | C2 | Particle Exposure | TPJLR.15.051 | 27-32 | 1.2 | Estimated from standard
Group C | C3 | Vibration | K15 | 27-32 | 4 | Timing plan reference
Group C | C4 | Dust Ingress | K13 | 27-32 | 2 | Timing plan reference
Group C | C5 | Dust Blowing | K14 | 27-32 | 0.2 | Estimated from standard
Group C | C6 | Mechanical Wear-Out | K26 | 27-32 | 23 | Timing plan reference
Group C | C7 | L1/L4 | TPJLR.18.125 L1/L4 | 27-32 | 2 | User confirmed
Group C | C8 | Optical Test | TPJLR-13-001 | 27-32 | 2 | User confirmed
Group C | C9 | Internal Inspection | L6 | 27-32 | 3 | Timing plan reference
D1 | D1-1 | Corrosive Gases | K21 | 33-38 | 42 | Timing plan reference
D1 | D1-2 | L1/L4 | TPJLR.18.125 L1/L4 | 33-38 | 2 | User confirmed
D1 | D1-3 | Optical Test | TPJLR-13-001 | 33-38 | 2 | User confirmed
D1 | D1-4 | Internal Inspection | L6 | 33-38 | 3 | Timing plan reference
D2 | D2-1 | Solar Radiation | K20 | 39-44 | 2 | Timing plan reference
D2 | D2-2 | L1/L4 | TPJLR.18.125 L1/L4 | 39-44 | 2 | User confirmed
D2 | D2-3 | Optical Test | TPJLR-13-001 | 39-44 | 2 | User confirmed
D2 | D2-4 | Internal Inspection | L6 | 39-44 | 3 | Timing plan reference
D3 | D3-1 | Thermal Shock Endurance | K23 | 45-52 | 46 | Timing plan reference
D3 | D3-2 | L1/L4 | TPJLR.18.125 L1/L4 | 45-52 | 2 | User confirmed
D3 | D3-3 | Internal Inspection | L6 | 45-52 | 20 | Timing plan reference
D4 | D4-1 | Dewing Test | K8 | 45-50 | 2 | Timing plan reference
D4 | D4-2 | L1/L4 | TPJLR.18.125 L1/L4 | 45-50 | 2 | User confirmed
D4 | D4-3 | Internal Inspection | L6 | 45-50 | 3 | Timing plan reference
D5 | D5-1 | High Temperature Endurance | K24 | 51-56 | 42 | Timing plan reference
D5 | D5-2 | L1/L4 | TPJLR.18.125 L1/L4 | 51-56 | 2 | User confirmed
D5 | D5-3 | Optical Test | TPJLR-13-001 | 51-56 | 2 | User confirmed
D5 | D5-4 | Internal Inspection | L6 | 51-56 | 3 | Timing plan reference
D6 | D6-1 | 85/85 HTHH Endurance | K27 | 65-70 | 42 | Timing plan reference
D6 | D6-2 | L1/L4 | TPJLR.18.125 L1/L4 | 65-70 | 2 | User confirmed
D6 | D6-3 | Internal Inspection | L6 | 65-70 | 3 | Timing plan reference
D7 | D7-1 | 60/95 HTHH Endurance | K27 | 57-62 | 46 | Timing plan reference
D7 | D7-2 | L1/L4 | TPJLR.18.125 L1/L4 | 57-62 | 2 | User confirmed
D7 | D7-3 | Optical Test | TPJLR-13-001 | 57-62 | 2 | User confirmed
D7 | D7-4 | Internal Inspection | L6 | 57-62 | 3 | Timing plan reference
D8 | D8-1 | HALT | K28 | 77-82 | No Test | Current MLA flow chart
D8 | D8-2 | L1/L4 | TPJLR.18.125 L1/L4 | 77-82 | No Test | Current MLA flow chart
D8 | D8-3 | Optical Test | TPJLR-13-001 | 77-82 | No Test | Current MLA flow chart
D8 | D8-4 | Internal Inspection | L6 | 77-82 | No Test | Current MLA flow chart
D9 | D9-1 | Condensing Humidity | TPJLR.52.351 | 63-68 | 5 | 120h from standard
D9 | D9-2 | L1/L4 | TPJLR.18.125 L1/L4 | 63-68 | 2 | User confirmed
D9 | D9-3 | Optical Test | TPJLR-13-001 | 63-68 | 2 | User confirmed
D9 | D9-4 | Internal Inspection | L6 | 63-68 | 3 | Aligned to other D groups
Group E | E | EMC Test Plan | JLR-EMC-CS | Per EMC plan | TBD | Duration TBD
Group F | F1 | Restricted Substance Management | STJLR.99.9999 | Based on actual tests | 40 | Timing plan reference
Group F | F2 | Operating Noise & Transient Noise | TPJLR.00.344 | 69-93 | 10 | Timing plan reference

## Timing Summary
Timing Summary
Group | Known Subtotal (d) | Comment
Baseline | 10 | Known subtotal
Group A | 95.4 | Known subtotal
Group B | 20 | Known subtotal
Group C | 51.4 | Known subtotal
D1 | 49 | Known subtotal
D2 | 9 | Known subtotal
D3 | 68 | Known subtotal
D4 | 7 | Known subtotal
D5 | 49 | Known subtotal
D6 | 47 | Known subtotal
D7 | 53 | Known subtotal
D8 | TBD/Partial | Known subtotal
D9 | 12 | Known subtotal
Group E | TBD/Partial | Known subtotal
Group F | 50 | Known subtotal

## Detailed List
Group | Seq | Test Item | Standard | Sample No. | Time (d) | Basis / Note
Baseline |  | Optical Test | TPJLR-13-001 / STJLR.13.5009 | 1-68 | 7 | Pre-test unified optical test
Baseline |  | L1/L4 | TPJLR.18.125 L1/L4 | 1-68 | 3 | Pre-test baseline functional/performance eval
Group A | A1 | Particle Exposure | TPJLR.15.051 | 1-12 | 1.2 | Estimated from standard
Group A | A2 | Low Temperature Exposure | K1 | 1-12 | 2 | Timing plan reference
Group A | A3 | High Temperature Exposure | K2 | 1-12 | 2 | Timing plan reference
Group A | A4 | Low Temperature Operation | K3 | 1-12 | 2 | Timing plan reference
Group A | A5 | High Temperature Operation | K4 | 1-12 | 5 | Timing plan reference
Group A | A6 | Temperature Step Test | K5 | 1-12 | 2 | Timing plan reference
Group A | A7 | Powered Thermal Cycle | K6 | 1-12 | 11 | Timing plan reference
Group A | A8 | Thermal Shock in Air | K7 | 1-12 | 14 | Timing plan reference
Group A | A9 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed
Group A | A10 | Vibration | K15 | 1-12 | 7 | Timing plan reference
Group A | A11 | Mechanical Shock - Package Drop | K16.1 | 1-14 | 2 | Timing plan reference
Group A | A12 | Mechanical Shock - Low | K16.4 | 1-12 | 2 | Timing plan reference
Group A | A13 | Audible Noise | K17 | 1-12 | 10 | Timing plan reference
Group A | A14 | Humidity Temperature Cycle | K9 | 1-12 | 12 | Timing plan reference
Group A | A15 | Water/Fluid Ingress | K10 | 1-12 | 3 | Timing plan reference
Group A | A16 | Dust Ingress | K13 | 1-12 | 5 | Timing plan reference
Group A | A17 | Dust Blowing | K14 | 1-12 | 0.2 | Estimated from standard
Group A | A18 | L1/L4 | TPJLR.18.125 L1/L4 | 1-12 | 3 | User confirmed
Group A | A19 | Optical Test | TPJLR-13-001 | 1-12 | 2 | User confirmed
Group A | A20 | Internal Inspection | L6 | 1-12 | 7 | Timing plan reference
Group B | B1 | Chemical Resistance | K22 | 15-26 | 5 | Timing plan reference
Group B | B2 | Connector and Lead/Lock Strength | K18 | 15-26 | 7 | Timing plan reference
Group B | B3 | L1/L4 | TPJLR.18.125 L1/L4 | 15-26 | 2 | User confirmed
Group B | B4 | Optical Test | TPJLR-13-001 | 15-26 | 2 | User confirmed
Group B | B5 | Internal Inspection | L6 | 15-26 | 4 | Timing plan reference
Group C | C1 | Thermal Shock in Air | K7 | 27-32 | 14 | Timing plan reference
Group C | C2 | Particle Exposure | TPJLR.15.051 | 27-32 | 1.2 | Estimated from standard
Group C | C3 | Vibration | K15 | 27-32 | 4 | Timing plan reference
Group C | C4 | Dust Ingress | K13 | 27-32 | 2 | Timing plan reference
Group C | C5 | Dust Blowing | K14 | 27-32 | 0.2 | Estimated from standard
Group C | C6 | Mechanical Wear-Out | K26 | 27-32 | 23 | Timing plan reference
Group C | C7 | L1/L4 | TPJLR.18.125 L1/L4 | 27-32 | 2 | User confirmed
Group C | C8 | Optical Test | TPJLR-13-001 | 27-32 | 2 | User confirmed
Group C | C9 | Internal Inspection | L6 | 27-32 | 3 | Timing plan reference
D1 | D1-1 | Corrosive Gases | K21 | 33-38 | 42 | Timing plan reference
D1 | D1-2 | L1/L4 | TPJLR.18.125 L1/L4 | 33-38 | 2 | User confirmed
D1 | D1-3 | Optical Test | TPJLR-13-001 | 33-38 | 2 | User confirmed
D1 | D1-4 | Internal Inspection | L6 | 33-38 | 3 | Timing plan reference
D2 | D2-1 | Solar Radiation | K20 | 39-44 | 2 | Timing plan reference
D2 | D2-2 | L1/L4 | TPJLR.18.125 L1/L4 | 39-44 | 2 | User confirmed
D2 | D2-3 | Optical Test | TPJLR-13-001 | 39-44 | 2 | User confirmed
D2 | D2-4 | Internal Inspection | L6 | 39-44 | 3 | Timing plan reference
D3 | D3-1 | Thermal Shock Endurance | K23 | 45-52 | 46 | Timing plan reference
D3 | D3-2 | L1/L4 | TPJLR.18.125 L1/L4 | 45-52 | 2 | User confirmed
D3 | D3-3 | Internal Inspection | L6 | 45-52 | 20 | Timing plan reference
D4 | D4-1 | Dewing Test | K8 | 45-50 | 2 | Timing plan reference
D4 | D4-2 | L1/L4 | TPJLR.18.125 L1/L4 | 45-50 | 2 | User confirmed
D4 | D4-3 | Internal Inspection | L6 | 45-50 | 3 | Timing plan reference
D5 | D5-1 | High Temperature Endurance | K24 | 51-56 | 42 | Timing plan reference
D5 | D5-2 | L1/L4 | TPJLR.18.125 L1/L4 | 51-56 | 2 | User confirmed
D5 | D5-3 | Optical Test | TPJLR-13-001 | 51-56 | 2 | User confirmed
D5 | D5-4 | Internal Inspection | L6 | 51-56 | 3 | Timing plan reference
D6 | D6-1 | 85/85 HTHH Endurance | K27 | 65-70 | 42 | Timing plan reference
D6 | D6-2 | L1/L4 | TPJLR.18.125 L1/L4 | 65-70 | 2 | User confirmed
D6 | D6-3 | Internal Inspection | L6 | 65-70 | 3 | Timing plan reference
D7 | D7-1 | 60/95 HTHH Endurance | K27 | 57-62 | 46 | Timing plan reference
D7 | D7-2 | L1/L4 | TPJLR.18.125 L1/L4 | 57-62 | 2 | User confirmed
D7 | D7-3 | Optical Test | TPJLR-13-001 | 57-62 | 2 | User confirmed
D7 | D7-4 | Internal Inspection | L6 | 57-62 | 3 | Timing plan reference
D8 | D8-1 | HALT | K28 | 77-82 | No Test | Current MLA flow chart
D8 | D8-2 | L1/L4 | TPJLR.18.125 L1/L4 | 77-82 | No Test | Current MLA flow chart
D8 | D8-3 | Optical Test | TPJLR-13-001 | 77-82 | No Test | Current MLA flow chart
D8 | D8-4 | Internal Inspection | L6 | 77-82 | No Test | Current MLA flow chart
D9 | D9-1 | Condensing Humidity | TPJLR.52.351 | 63-68 | 5 | 120h from standard
D9 | D9-2 | L1/L4 | TPJLR.18.125 L1/L4 | 63-68 | 2 | User confirmed
D9 | D9-3 | Optical Test | TPJLR-13-001 | 63-68 | 2 | User confirmed
D9 | D9-4 | Internal Inspection | L6 | 63-68 | 3 | Aligned to other D groups
Group E | E | EMC Test Plan | JLR-EMC-CS | Per EMC plan | TBD | Duration TBD
Group F | F1 | Restricted Substance Management | STJLR.99.9999 | Based on actual tests | 40 | Timing plan reference
Group F | F2 | Operating Noise & Transient Noise | TPJLR.00.344 | 69-93 | 10 | Timing plan reference